Hospital Patient Agile Workshop

Hospital Patient Referral Treatment and Administration System

Group Project Planning Pack

Based on the supplied Case Study and Agile Workshop brief | Version 1.0 | 15 September 2026

Document Use

This planning pack converts the supplied case study into prioritised, assignable, demonstrable and testable Agile work. Owners use Blackboard display names. Any item labelled “To be confirmed with Tutor/Stakeholder” is not a stated case-study fact: it requires confirmation before implementation, or an explicitly approved and documented project assumption.

| Blackboard Name | UWE ID | Suggested Project Responsibility | To be Confirmed |
| --- | --- | --- | --- |
| logren Li | 23084430 | Business analysis: requirements traceability, stakeholder map, use cases and acceptance criteria. | Final team allocation. |
| Jin Wang | 23084417 | Workflow development: BPMN, Camunda workflow, task states and exceptions. | Whether Camunda is required and its permitted version. |
| Leo Zhu | 23084429 | Integration development: scheduling, correspondence and payment service mocks and interface tests. | Protocols, sandbox access and authentication approach. |
| Jackson Yang | 23084428 | Quality and security: testing, RBAC, audit trail, data protection and evidence. | Test environment and permitted de-identified data. |
| Zhenghong Guo | 23084426 | Project and reporting: Sprint coordination, reporting, demonstration and pathway monitoring. | Sprint length and assessment emphasis. |

1 Case Study Summary

The specialist hospital service manages a patient pathway from referral by a General Practitioner or another hospital through consultation, diagnosis, treatment, follow-up care and continuing communication. Medical Secretaries, the Outpatient Bookings Team, Call Handling Team, Clinical Nurse Specialist Team, Clinical Nurse Specialist Administrative Support Team, Treatment and Chemotherapy Bookings Team, Patient Pathway Coordinators, Consultants and other clinical professionals, Finance Team and Administrative Management Team must exchange accurate and timely information. The proposed Hospital Patient Administration System is intended to replace fragmented use of existing hospital systems, electronic forms, email, telephone calls, letters and manually maintained records. Its purpose is to improve coordination, make delays visible and maintain a complete audit trail without confusing clinical, administrative and financial authority.

The main pathway starts when Medical Secretaries receive a referral. They check whether expected supporting material, such as previous clinic letters, investigation results and diagnostic reports, is present. They may request missing information from the referring organisation, but they must not assess clinical suitability. The referral then goes to the appropriate Consultant, who may accept, reject, request further information or redirect it to another specialist service. The system must record the decision, the reason and the decision maker. A New Patient Appointment may only be arranged after an authorised Consultant has accepted the referral.

For an accepted referral, the Outpatient Bookings Team receives specialty, priority, preferred timeframe and relevant patient requirements, and uses an external scheduling service. The booking is confirmed in the hospital system and the patient is normally informed by an external correspondence service. If the appointment is due within two weeks, the patient must also be contacted by telephone. Every contact attempt and outcome must be recorded, including unanswered calls, incorrect numbers and requests for a different appointment. Urgent referrals and cases with no suitable appointment in the clinician-requested period are explicit exceptions.

At the New Patient Appointment, the Consultant and clinical team assess the patient and discuss diagnosis and treatment options. If the patient agrees, the Consultant records consent and creates an authorised Treatment Booking Request with treatment, start date, cycle count and frequency, reviews between cycles and special resources. Administrative staff must not process an incomplete or unauthorised request. The Treatment or Chemotherapy Bookings Team coordinates hospital and external treatment, laboratory, imaging and scheduling dependencies. An unavailable external service leaves the booking pending, notifies the responsible team and records further attempts without creating duplicate appointments.

Before treatment confirmation, the system establishes whether hospital funding, approved insurer or funding organisation coverage, or direct patient payment applies. Finance records funding organisation, authorisation reference, approved amount and limitations. When payment is needed, a secure request goes to an external Payment Service Provider (PSP); the system must not store complete card details. Advance-payment treatment normally cannot be confirmed until successful payment, funding approval, an exemption or a payment arrangement is recorded. Declined, cancelled, duplicated or incomplete payments require notification. A successful PSP payment without a returned confirmation must be investigated, never automatically charged again. Urgent treatment can proceed after clinical authorisation when delay risks the patient, but its reason must be recorded and sent to Finance for follow-up.

Consultants remain responsible for clinical decisions, chemotherapy fitness, treatment changes and Clinic Letter clinical content. Finance alone makes funding and refund decisions within its authority and must not decide clinical necessity. Administrative teams coordinate records, bookings and communication but cannot diagnose, determine clinical suitability or make financial authorisations. Other key processes are enquiry classification and routing; Clinic Letter drafting, approval, distribution, reminders and escalation; follow-up booking; cancellation and non-attendance; role-based access control (RBAC); immutable audit logging; controlled back-entry after downtime; and pathway reporting. To be confirmed with Tutor/Stakeholder are urgency criteria, contact retry rules, duplicate matching rules, interface specifications and service levels, payment/refund policies, downtime reconciliation, data retention and communication accessibility rules. For the prototype, these are explicitly represented by configurable fields, mock services and visible manual investigation queues rather than invented policy.

Stakeholder Map and Authority Boundaries

| Stakeholder | Goal | Permitted Responsibility | Must Not Decide or Change | Evidence |
| --- | --- | --- | --- | --- |
| Medical Secretaries | Complete and traceable referrals and letters. | Check documents, request missing information and administratively process approved letters. | Clinical suitability or the clinical meaning of a letter. | Document checklist, request record, processing history. |
| Consultant / authorised clinician | Safe, clinically appropriate patient pathway. | Referral decision, treatment authorisation, clinical letter approval and urgent clinical decision. | Financial refund approval unless separately financially authorised. | Authorisation, decision reason and clinical review record. |
| Booking Teams | Correct appointments and treatment bookings. | Schedule only authorised requests; record contact and external-service attempts. | Diagnosis, clinical necessity or fitness-to-treat decision. | Appointment record, service response and retry log. |
| Finance Team | Accountable funding, payment and refund handling. | Record funding; manage payment; approve refunds within financial authority. | Clinical necessity, treatment suitability or chemotherapy fitness. | Funding record, PSP transaction and refund result. |
| Call Handling Team | Safe enquiry triage. | Answer authorised administrative information and route enquiries. | Diagnosis, result interpretation, treatment recommendation or clinical advice. | Classification, routing and closure record. |
| Pathway Coordinators / Managers | Identify and resolve delay. | Monitor, remind, escalate and report. | Replace clinical or financial authorisation. | Reminder, escalation and report history. |

2 Main Deliverables

| Deliverable | Purpose | Main Content | Acceptance Evidence |
| --- | --- | --- | --- |
| Stakeholder Map | Clarify goals, information needs and authority boundaries. | Stakeholders, interests, responsibilities, conflicts and authority/RACI boundary. | Reviewed map; clinical, administrative and financial boundary traceable to case study. |
| Main and Exception BPMN | Visualise end-to-end flow and decisions. | Referral to follow-up; missing data, rejection, no slot, service failure, payment exception, refund and letter escalation. | BPMN diagrams; each gateway has an explained rule; peer walkthrough record. |
| Use Case Diagram / Descriptions | Define actor-system interactions. | Referral review, booking, treatment, payment, letters, enquiries and follow-up. | Diagram and descriptions with preconditions, main flow, exceptions and postconditions. |
| Functional Requirements | Turn the case into buildable behaviours. | Numbered FRs, roles, inputs, rules, outputs and acceptance criteria. | Baseline requirements; each requirement linked to a Backlog ID. |
| Non-functional Requirements | Define security, availability, audit and privacy constraints. | RBAC, non-editable audit, external protection, downtime capture and availability assumptions. | NFR list with verification method and confirmation gaps. |
| Data Model / ERD | Maintain patient pathway and financial relationships. | Patient, Referral, Document, Decision, Appointment, TreatmentRequest, Funding, Payment, Refund, Letter, Enquiry and AuditEvent. | ERD with key relationships, uniqueness and idempotency constraints. |
| Camunda Workflow or Prototype | Demonstrate operating controls. | States, forms, authorisation gateways, human tasks, exception queues and audit points. | Runnable demonstration or clickable prototype; screenshots/recording and tests. |
| External Integration Design | Control dependencies, failure and duplicate submission. | Scheduling, correspondence, clinical/treatment and PSP contracts, timeout, retry, idempotency and manual handling. | Interface contract or mock; failed-service test evidence. |
| Test Plan, Cases and Evidence | Prove acceptance criteria. | Risk-based normal, exception, permission and regression tests, defects and results. | Plan, cases, screenshots/logs and defect closure record. |
| Project Demonstration Pack | Show the integrated increment and decisions. | Demo script, process/architecture diagrams, Sprint evidence, limitations and next steps. | Slides/recording, review checklist and feedback record. |

3 Product Backlog

Estimates use person-days (pd) for relative planning only; they are not case-study deadlines. Status is Planned until changed by the team at Sprint Planning. “To be confirmed with Tutor/Stakeholder” remains visible rather than being treated as a rule.

Product Backlog Detail

| ID | Task Title | Description | Priority | Related Requirement or Business Rule | Estimate | First Owner | Second Owner | Dependencies | Acceptance Conditions | Evidence Required | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PB01 | Receive referral and check documents | Register referral source, patient identity and supporting documents; flag missing items. | Must | Secretaries check documents, not clinical suitability. | 2 pd | logren Li | Jackson Yang | ERD; RBAC | Missing items are explicit; a request task can be created; no clinical decision field is available. | Form capture, missing-data test, audit event | Planned |
| PB02 | Record Consultant referral decision | Support accept, reject, request information and redirect, with reason and decision maker. | Must | Only an authorised Consultant makes the clinical decision. | 2 pd | Jin Wang | logren Li | PB01; RBAC | All four decisions save; non-Consultant access is denied; user, time and reason are auditable. | Workflow, negative permission test, audit log | Planned |
| PB03 | Guard New Patient Appointment eligibility | Send only accepted referrals to the booking queue. | Must | Appointment follows authorised Consultant acceptance only. | 1 pd | Jin Wang | Jackson Yang | PB02 | Unaccepted, rejected and information-pending referrals cannot create a booking request; accepted referrals can. | State-transition test | Planned |
| PB04 | Book first appointment through external scheduling | Use an external scheduling service with specialty, priority, timeframe and patient requirements. | Must | No suitable slot must be highlighted and referred, not silently booked late. | 3 pd | Leo Zhu | Jin Wang | PB03; scheduling mock | A successful response creates one appointment only; no-slot response creates a visible escalation task. | Mock log, UI and exception test | Planned |
| PB05 | Notify appointment and call within two weeks | Send correspondence and create a phone task for an appointment within the next two weeks. | Must | Letter normally; telephone contact additionally within two weeks. | 2 pd | Leo Zhu | logren Li | PB04; correspondence mock | 0-14 day appointment produces both notification and phone task; 15-day boundary does not trigger this rule. | Boundary test, contact record | Planned |
| PB06 | Handle failed contact and rescheduling | Record unanswered call, incorrect number, alternative request and outcome. | Must | Every contact attempt and outcome is recorded. | 2 pd | logren Li | Jin Wang | PB05 | Each attempt retains timestamp, user and result; rescheduling preserves original appointment history. | Contact log, reschedule regression test | Planned |
| PB07 | Handle urgent referral and no slot | Make urgent work visible and escalate no-slot cases. | Must | Urgent cases cannot wait for normal administration; no-slot is highlighted. | 2 pd | Jin Wang | logren Li | PB03; urgency rules TBC | Urgent label creates high-priority task; no slot records reason and receiving pathway team; criteria remain TBC. | BPMN, queue screenshot, walkthrough | Planned |
| PB08 | Create authorised Treatment Booking Request | Record consent, treatment, date, cycles, reviews and resources. | Must | Unauthorised or incomplete requests must not be processed administratively. | 3 pd | Jin Wang | logren Li | PB02; RBAC | Only authorised clinical role submits; missing or unauthorised request cannot enter booking queue. | Form validation, permission test, audit log | Planned |
| PB09 | Coordinate treatment booking and external failure | Book using hospital or external services and handle unavailability. | Must | Failure leaves booking pending, notifies team and records retries without duplicate appointments. | 3 pd | Leo Zhu | Jin Wang | PB08; integration mock | Timeout/failure remains pending; every attempt is retained; same request cannot create duplicate appointment. | Failure log, idempotency test, notification | Planned |
| PB10 | Record funding approval | Record organisation, approval reference, approved amount and limitations. | Must | Finance records funding approval. | 2 pd | logren Li | Jackson Yang | ERD; RBAC | Only Finance creates/edits approval; all fields are auditable; limits link to treatment request. | Permission test, data capture, audit | Planned |
| PB11 | Initiate secure payment request | Obtain charge and send minimum necessary request to PSP without storing complete card data. | Must | System must not store complete card or unnecessary financial details. | 3 pd | Leo Zhu | Jackson Yang | PB10; PSP mock | Request has amount and idempotency key; model/log review has no complete card data; authorised flow only. | Contract sample, field review, security check | Planned |
| PB12 | Process payment status and prevent duplicate payment | Handle success, declined, cancelled and incomplete; allow safe retry. | Must | Advance payment normally blocks confirmation until resolved; no duplicate charge or booking. | 3 pd | Leo Zhu | Jin Wang | PB11; PB09 | Replay of same payment intent adds no charge; failure notifies patient and administration; success removes payment block. | Replay test, notification, transaction log | Planned |
| PB13 | Investigate missing payment callback | Create an investigation when PSP success is not returned to hospital. | Must | Never automatically request another payment. | 2 pd | Leo Zhu | Jackson Yang | PB11 | Timeout is Investigation; no new payment request is created; Finance can record resolution. | Missing-callback test, queue, audit | Planned |
| PB14 | Process refund | After cancellation, postponement or change, authorised Finance decides and sends refund to PSP. | Must | Clinical staff cannot approve refund solely by clinical role; result is recorded. | 3 pd | Leo Zhu | logren Li | PB12; financial authority | Unauthorised approver is denied; full/partial amount and reason retained; PSP result links to original transaction. | Negative permission test, refund mock, linkage | Planned |
| PB15 | Handle treatment modification and urgent exception | Accept formally authorised modification only; support urgent postponement with subsequent authorisation. | Must | Informal email/telephone cannot change treatment; finance impact is referred. | 3 pd | Jin Wang | Jackson Yang | PB08; PB10 | Unauthorised input cannot change schedule; urgent action records clinician, reason and follow-up; Finance receives charge-impact task. | Exception BPMN, tests, audit | Planned |
| PB16 | Review chemotherapy cycle | Require clinical review and blood-test input before subsequent cycle decision. | Must | Only clinical team decides continue, delay or change. | 2 pd | Jin Wang | Jackson Yang | PB08; clinical result interface TBC | Non-clinical role cannot decide; cycle is not confirmed before clinical decision; decision is traceable. | RBAC test, state model, audit | Planned |
| PB17 | Classify and route patient enquiries | Record source, category, priority, owner, response and resolution. | Must | Every enquiry is recorded, classified, prioritised and routed. | 2 pd | logren Li | Jin Wang | RBAC; urgency rules TBC | Every enquiry has required routing fields; clinical category goes only to clinical queue; urgency rule is clearly TBC. | Form, routing test, report sample | Planned |
| PB18 | Prevent Call Handler clinical overreach | Route clinical, financial and administrative enquiries by authority. | Must | Call Handler cannot diagnose, interpret results, recommend treatment or give clinical advice. | 1.5 pd | Jackson Yang | logren Li | PB17; RBAC | Call Handler sees authorised administrative answer only; clinical category cannot contain advice and is routed to clinician. | Permission matrix, negative test | Planned |
| PB19 | Draft and approve Clinic Letter | Record drafting, completion, clinical approval and recipients. | Must | Consultant approves clinical content before distribution. | 3 pd | Jin Wang | logren Li | PB02; RBAC | Unapproved letter cannot distribute; secretary cannot alter clinical meaning; suspected error returns to Consultant. | State test, permission test, audit | Planned |
| PB20 | Send Clinic Letter and manage reminders | Record processing/distribution dates and method; implement 7-day delay and escalation. | Must | Avoid repeated reminders after completion; weekly reminder, one-month and three-month escalation. | 3 pd | Jin Wang | Zhenghong Guo | PB19; correspondence mock | Date-driven reminder/escalation works; completed letter receives no new reminder; full history retained. | Time-based test, reminder log, report | Planned |
| PB21 | Book follow-up and handle cancellation/no-show | Book from clinical request and record cancellation, decline and non-attendance. | Must | Outside timeframe is highlighted; clinical continuation/discharge decision is not administrative. | 3 pd | Leo Zhu | logren Li | PB04; PB10 | No-slot case is escalated; cancellation/no-show does not create clinical decision; paid case routes to Finance. | Workflow demo, exception test, route log | Planned |
| PB22 | Implement authentication and RBAC | Apply minimum access required for sensitive clinical and financial information. | Must | User authentication and role-based access are required. | 3 pd | Jackson Yang | Jin Wang | Authority matrix | Unauthorised role is denied; role boundary matches case; record access is logged. | Matrix, positive/negative tests, access log | Planned |
| PB23 | Implement immutable audit and downtime back-entry | Record user, date, time and action; control activity recorded during outage. | Must | Ordinary users cannot edit audit records; availability needs a back-entry procedure. | 3 pd | Jackson Yang | Jin Wang | PB22; data model | Audit has four attributes and ordinary user cannot edit; back-entry includes original time, entrant and reason. | Audit export, tamper test, back-entry test | Planned |
| PB24 | Create pathway reports and monitoring | Report volumes, waits, contact failures, letters, enquiries, bookings, funding, payments, refunds and pathway progress. | Should | Management requires listed operational and pathway reports. | 3 pd | Zhenghong Guo | Jackson Yang | PB01-PB23 data | Every listed measure is filterable/exportable; empty data shows zero/blank without invented figures. | Report screenshots, data reconciliation | Planned |
| PB25 | Run end-to-end testing and demonstration | Test normal, exception, permission, audit and integration scenarios; prepare review evidence. | Must | Workshop requires integrated increment, test evidence, feedback and backlog update. | 3 pd | Jackson Yang | Zhenghong Guo | PB01-PB24 | At least one E2E normal path and every high-risk exception have repeatable evidence; limitations are explicit. | Test report, recording, demo script, feedback | Planned |

4 Task Breakdown

Every task is small enough to complete and review in one Sprint. Definition of Done requires a model or implementation artefact, a focused verification result and traceable evidence.

| Task ID | Backlog ID | Task Description | Owner | Dependencies | Definition of Done |
| --- | --- | --- | --- | --- | --- |
| T01 | PB01 | Define Referral, Document and missing-information states and validation rules. | logren Li | ERD draft | Data dictionary reviewed; missing state is distinct; requirement link recorded. |
| T02 | PB01 | Implement document checklist and missing-information request task. | Jin Wang | T01; RBAC | Secretary can request information; no clinical decision control exists; audit screenshot saved. |
| T03 | PB02 | Model Consultant accept, reject, request-information and redirect BPMN gateway. | Jin Wang | PB01 | Four outcomes and decision reason/data are shown; analyst walkthrough passes. |
| T04 | PB02 | Implement clinical decision form and test non-Consultant denial. | Jackson Yang | T03; RBAC | All outcomes submit; unauthorised access fails; audit includes user, time and reason. |
| T05 | PB03 | Configure Accepted-to-booking-request state transition. | Jin Wang | T04 | Only Accepted proceeds; negative states fail; state model updated. |
| T06 | PB03 | Validate specialty, priority, timeframe and patient requirements in booking request. | logren Li | T05 | All four fields present; missing field blocks send; test evidence filed. |
| T07 | PB04 | Define scheduling mock contract for success, no-slot and timeout. | Leo Zhu | T06 | Versioned request/response examples; no-slot and timeout have explicit states. |
| T08 | PB04 | Implement appointment creation and no-slot escalation queue. | Leo Zhu | T07 | Success creates one appointment; no slot routes to pathway queue without silent late booking. |
| T09 | PB05 | Implement correspondence notification event and retain channel/result. | Leo Zhu | T08 | Confirmed appointment creates notification; result is traceable; failure is visible. |
| T10 | PB05 | Implement within-14-days phone task and date-boundary test. | logren Li | T08 | 0-14 days creates task; 15 days does not; result recorded. |
| T11 | PB06 | Design immutable contact-attempt, outcome and rescheduling history. | logren Li | T10 | Every attempt retains time, user and outcome; reschedule retains previous data. |
| T12 | PB06 | Implement unanswered, wrong-number and alternative-slot routing. | Jin Wang | T11 | Three outcomes route correctly; no duplicate booking; demo repeatable. |
| T13 | PB07 | Document urgency-rule gap and create high-priority manual queue prototype. | Jin Wang | T05 | Rule is marked TBC; urgent flag is visible and notifies assigned queue. |
| T14 | PB07 | Test combined no-slot and urgent escalation record. | Jackson Yang | T13 | Test proves record and notification; no unconfirmed time limit is claimed. |
| T15 | PB08 | Define Treatment Booking Request mandatory fields and clinical authorisation state. | logren Li | T04 | Treatment, date, cycles, review, resource and consent captured; authoriser required. |
| T16 | PB08 | Implement gate that blocks administrative processing of unauthorised request. | Jin Wang | T15; RBAC | Unauthorised request cannot enter booking; authorised path passes; evidence attached. |
| T17 | PB09 | Define treatment-service idempotency key and pending state. | Leo Zhu | T16 | Same request key is stable; failure stays pending; retry contract documented. |
| T18 | PB09 | Implement failure notification, retry history and duplicate-booking regression test. | Leo Zhu | T17 | Every attempt has result/time; replay creates no duplicate; responsible team is notified. |
| T19 | PB10 | Extend ERD to link Funding Approval and Treatment Request. | logren Li | T15 | Organisation, reference, amount and limits modelled; quality review passes. |
| T20 | PB10 | Implement Finance-only funding approval edit permission and audit. | Jackson Yang | T19; RBAC | Non-Finance edit fails; Finance action audited; validation passes. |
| T21 | PB11 | Define PSP minimum request fields and prohibited-data list. | Leo Zhu | T19 | Amount, reference and idempotency key present; complete card data explicitly excluded. |
| T22 | PB11 | Implement authorised secure payment mock request. | Leo Zhu | T21; RBAC | Only authorised flow sends; mock receives minimum fields; log exposes no card data. |
| T23 | PB12 | Implement success, declined, cancelled and incomplete payment state machine. | Jin Wang | T22 | State visible; payment block remains until success/resolution; transition audited. |
| T24 | PB12 | Execute duplicate-payment replay and duplicate-booking regression tests. | Jackson Yang | T23; T18 | Repeated intent records one payment and no new appointment; result repeatable. |
| T25 | PB13 | Implement missing-callback Investigation queue and no-auto-retry rule. | Leo Zhu | T22 | Timeout enters Investigation; no second payment request; Finance sees task. |
| T26 | PB13 | Test PSP-success-but-callback-missing end-to-end scenario. | Jackson Yang | T25 | Transaction is Investigation; no second charge; audit chain is complete. |
| T27 | PB14 | Define refund request, approval, PSP result and original-transaction linkage. | logren Li | T23 | Full/partial amount, reason and original transaction retained; policy gaps labelled TBC. |
| T28 | PB14 | Implement Finance-authority approval and PSP refund callback record. | Leo Zhu | T27; RBAC | Clinical-only role denied; authorised Finance approves; result audited. |
| T29 | PB15 | Model formal modification, informal rejection, urgent hold and Finance referral BPMN. | Jin Wang | T16; T20 | All paths complete; informal input cannot alter schedule; urgent path has follow-up task. |
| T30 | PB15 | Implement modification form, clinical authorisation check and finance-impact notification. | Jin Wang | T29 | Only authorised form changes schedule; reason/authoriser captured; finance task created if needed. |
| T31 | PB16 | Define chemotherapy review prerequisites and clinical decision states. | logren Li | T15 | Review/test reference plus continue/delay/change defined; interface gap marked TBC. |
| T32 | PB16 | Test Booking and Finance roles cannot confirm later cycle. | Jackson Yang | T31; RBAC | Both unauthorised tests fail; clinician path passes; audit retained. |
| T33 | PB17 | Design Enquiry category, priority, owning queue and closure fields. | logren Li | ERD | Received time, handler, queue, response and resolution required; urgency is TBC. |
| T34 | PB17 | Implement administrative, financial and clinical enquiry routing. | Jin Wang | T33; RBAC | Three categories route correctly; clinical item cannot remain with Call Handler. |
| T35 | PB18 | Create Call Handler permitted-answer and restricted-field matrix. | Jackson Yang | T33; RBAC | Matrix prohibits diagnosis, interpretation and treatment advice; restricted fields unavailable. |
| T36 | PB18 | Run Call Handler clinical-advice overreach negative test. | Jackson Yang | T35 | Attempt fails and logs security event; alternative route is clinical queue. |
| T37 | PB19 | Define Clinic Letter draft, completed, approved, processed and sent states. | Jin Wang | T04 | States and owners defined; approval required before send; clinical error returns. |
| T38 | PB19 | Implement Consultant approval and Secretary administrative-check separation. | Jackson Yang | T37; RBAC | Consultant only approves; Secretary cannot amend clinical meaning; actions audited. |
| T39 | PB20 | Implement seven-day delay and weekly reminder based on appointment date. | Jin Wang | T37 | Unfinished/unapproved after seven days is delayed; reminder cadence test passes. |
| T40 | PB20 | Implement one-month/three-month escalation and completion suppression test. | Jackson Yang | T39 | Escalations reach case-specified management levels; completion stops repeat reminders; history retained. |
| T41 | PB21 | Implement follow-up request to scheduling service with timeframe validation. | Leo Zhu | T08 | Clinical timeframe sent; no slot routes to pathway team; no silent late booking. |
| T42 | PB21 | Implement cancellation, decline and no-show record with Finance/clinical routing. | logren Li | T41; T20 | Event retained; payment case routes Finance; administration makes no clinical decision. |
| T43 | PB22 | Create minimum-privilege RBAC matrix and authentication entry point. | Jackson Yang | Stakeholder Map | Every case role gets minimum access; sensitive data restricted; review passes. |
| T44 | PB22 | Execute key-role positive and negative access tests. | Jackson Yang | T43 | Secretary, Consultant, Booking, Finance and Call Handler each have one positive and negative test. |
| T45 | PB23 | Define AuditEvent model and significant-action capture points. | logren Li | ERD; T43 | User, date, time and action present; covers material case actions. |
| T46 | PB23 | Implement non-editable audit and downtime back-entry form. | Jin Wang | T45 | Ordinary user cannot alter audit; entry includes original time, entrant and reason; quality verifies. |
| T47 | PB24 | Define report measures, source fields and no-data behaviour. | Zhenghong Guo | PB01-PB23 | Every case-listed measure maps to data; no data is not invented. |
| T48 | PB24 | Implement pathway-monitoring report and reconcile displayed figures. | Zhenghong Guo | T47 | Measures display/export; sample data reconciles to detail. |
| T49 | PB25 | Write risk-based E2E test plan and evidence index. | Jackson Yang | T01-T48 | Normal, exception, permission, audit and integration covered; every case has expected result/evidence location. |
| T50 | PB25 | Record integrated demo and update Backlog, limitations and feedback. | Zhenghong Guo | T49 | Demo shows true status; incomplete/TBC items transparent; feedback captured. |

5 Dependency Mapping

| Critical Flow | Predecessors | Dependent Work | Notify if Delayed | Fallback or Risk Mitigation |
| --- | --- | --- | --- | --- |
| Referral review to first appointment | T01-T06 | T07-T14; T37 | Outpatient Bookings, Consultant, Pathway Coordinator | Use state-controlled mock; never bypass Accepted gateway. |
| External scheduling service | T07 | T08-T12; T17-T18; T41-T42 | Booking Teams, Pathway Coordinator, Leo Zhu | Controlled mock; pending/no-slot queues; record retries and prevent duplicate booking. |
| Clinical treatment authorisation | T15-T16 | T17-T18; T29-T32 | Consultant, Treatment Booking Team, Jin Wang | Block administration until authorised; urgent hold has separate documented exception. |
| Funding and payment | T19-T22 | T23-T28; T42 | Finance Team, Leo Zhu, Jackson Yang | PSP mock; idempotency key, investigation queue and manual reconciliation; never auto-charge again. |
| RBAC and audit | T43-T46 | T04, T16, T20, T28, T32, T36, T38, T44, T49 | Whole team and Tutor | Deliver matrix and audit schema first; record prototype limitation if platform cannot enforce a control. |
| Clinic Letter timing | T37-T40 | T47-T50 | Consultants, Medical Secretaries, Pathway Coordinator, Administrative Manager | Use controlled clock/test data for 7-day, 1-month and 3-month checks; completion cancels later reminders. |
| Reporting and demonstration | T47-T50 | Sprint Review and final demonstration | Tutor and all group members | Fix a minimum data set; each metric reconciles to detail; display unavailable data as unavailable. |

6 Sprint Backlogs

Sprint 1 Requirements Roles Process Modelling and Foundation Prototype

| Item | Content |
| --- | --- |
| Sprint Goal | Establish a reviewable requirements baseline, authority boundaries, main/exception BPMN, ERD, RBAC/audit foundation and a minimum referral-to-clinical-decision flow. |
| Selected Backlog Items | PB01, PB02, PB03, PB07, PB08, PB10, PB17, PB18, PB19, PB22 and PB23. |
| Task Allocation | logren Li: T01, T06, T15, T19, T33, T45. Jin Wang: T02, T03, T05, T13, T16, T37. Jackson Yang: T04, T14, T20, T35, T36, T38, T43, T44, T46. Zhenghong Guo: requirements traceability and review preparation. |
| Dependencies and Risks | Urgency criteria, detailed role permissions, retention, and clinical-results interface are not provided. Mitigation: make them visible as TBC fields and manual queues. |
| Sprint Review Integrated Increment | Receive referral, document check, four Consultant decisions, Accepted-only booking request, authorised treatment request, RBAC denial, audit event, enquiry routing and Clinic Letter state. |
| Testing or Evidence | Stakeholder Map, BPMN walkthrough, FR/NFR traceability, permission tests, state-transition tests and audit export. |

Sprint 2 Core Referral Booking Treatment Authorisation and External Services

| Item | Content |
| --- | --- |
| Sprint Goal | Deliver executable first appointment, treatment and follow-up booking/notification happy paths and external-service failure controls without duplicate appointments. |
| Selected Backlog Items | PB04, PB05, PB06, PB09, PB15, PB16 and PB21. |
| Task Allocation | Leo Zhu: T07, T08, T09, T17, T18, T41. logren Li: T10, T11, T31, T42. Jin Wang: T12, T29, T30. Jackson Yang: T24 appointment-duplicate portion and T32. Zhenghong Guo: integration evidence index. |
| Dependencies and Risks | Scheduling, correspondence and treatment interface details are not supplied. Mitigation: versioned mock contracts and fixed mapping of no-slot/timeout/failure to visible queues. |
| Sprint Review Integrated Increment | Accepted referral scheduling, two-week phone rule, failed contact/reschedule, no-slot escalation, authorised treatment booking, service retry without duplicate booking, formal treatment modification, cycle review and follow-up cancellation/no-show routing. |
| Testing or Evidence | Interface contracts, mock success/no-slot/timeout logs, date-boundary test, appointment idempotency, clinical-permission negative tests and exception BPMN. |

Sprint 3 Payments Exceptions Audit Reporting Testing and Final Integration

| Item | Content |
| --- | --- |
| Sprint Goal | Complete funding, payment, refund and high-risk exception handling; integrate audit/reporting; finish with repeatable end-to-end evidence. |
| Selected Backlog Items | PB11, PB12, PB13, PB14, PB20, PB24 and PB25; retest PB22 and PB23. |
| Task Allocation | Leo Zhu: T21, T22, T25, T28. Jin Wang: T23, T39. logren Li: T27. Jackson Yang: T24, T26, T40, T49. Zhenghong Guo: T47, T48, T50. |
| Dependencies and Risks | Charge/refund policy, PSP callback contract and real data are unavailable. Mitigation: fixed de-identified mock data; missing success callback always becomes Investigation, never a second charge. |
| Sprint Review Integrated Increment | Funding approval, payment request/status, duplicate-payment prevention, missing-callback investigation, authorised refund, Clinic Letter reminder escalation/suppression, pathway report and auditable E2E chain. |
| Testing or Evidence | PSP mock transaction/refund result, idempotency replay, access tests, immutable-audit test, report reconciliation, E2E recording, known limitations and feedback list. |

7 Standup and Sprint Review Preparation

Individual Daily Standup Template

| Field | What the Individual Reports | Example Completion Evidence |
| --- | --- | --- |
| Completed today | Task ID, observable artefact and whether DoD is met. | “T18: service failure remains pending; interface log and regression test attached.” |
| Next action | Specific verb-led task and expected completion condition. | “Execute T24 payment replay test and save evidence of one transaction and no new appointment.” |
| Blocker | Fact, affected task, action already tried and decision needed. | “PSP callback fields are unavailable for T25; Tutor confirmation or mock-contract approval needed.” |
| Second-owner support | Who is needed, what review/pairing/test is required and when. | “Request Jackson Yang to peer-review idempotency assertions for 20 minutes.” |
| Handover | State, artefact/evidence location and receiving owner. | “T07 contract v0.2 reviewed; hand over to Leo Zhu for T08 implementation.” |

Group Sprint Review Checklist

□ State whether the Sprint Goal is met and show completed and unfinished PBIs.

□ Demonstrate one integrated end-to-end scenario, not isolated pages or unit-test screenshots.

□ Demonstrate at least one exception: missing documents, rejection, no slot, service failure, missing payment callback or unauthorised access.

□ Show the distinction between Consultant, administrative and Finance authority, including prohibited decisions.

□ Show audit trail with user, date, time and action, plus ordinary-user inability to edit it.

□ Show repeatable prevention evidence for duplicate appointment or duplicate payment.

□ State every item To be confirmed with Tutor/Stakeholder, the current assumption and scope impact.

□ Show test outcome, defects/limitations, feedback and Product Backlog update.

Completion Evidence Checklist

| Category | Evidence to Archive |
| --- | --- |
| Requirements and modelling | Stakeholder Map, numbered FR/NFR list, BPMN/Use Case/ERD versions, review record and assumption log. |
| Implementation and integration | Camunda screenshots or deployment notes, prototype link/recording, interface contracts, mock request/responses and configuration notes. |
| Quality and security | Test plan, cases, result screenshots/logs, defect list, RBAC matrix, negative permission tests, audit export and field review. |
| Agile collaboration | Product Backlog, task board, Sprint Backlog, Daily Standups, risk/dependency mapping and handover records. |
| Demonstration and feedback | Sprint Review script, E2E recording, slides, Tutor/peer feedback, backlog adjustment and unresolved-question list. |

Appendix A Items To Be Confirmed with Tutor Stakeholder

| Question to Confirm | Testable Prototype Assumption Only | Decision Owner |
| --- | --- | --- |
| What are the urgency categories and response timeframes for clinical concerns? | Represent urgent as a manual high-priority flag and queue; do not encode clinical thresholds. | Tutor, Consultant, Clinical Nurse Specialist Team |
| How many telephone retries, at what intervals, are required? | Record every attempt and outcome; do not automatically close the pathway before policy confirmation. | Outpatient Bookings Team, Tutor |
| What fields/time window define duplicate appointment and duplicate payment? | Use referral/treatment-request plus timeslot idempotency for appointment and payment-intent idempotency for payment. | Booking Teams, Finance Team, Tutor |
| What are external service interfaces, SLA, authentication and error codes? | Mock success, no-slot, timeout and failure; every failure enters visible queue with retry history. | IT/Integration Stakeholder, Tutor |
| How are charges, refund proportions and financial-authority thresholds determined? | Use fixed mock amount and manual Finance approval; do not infer real charge/refund policy. | Finance Team, Tutor |
| How should outage back-entry and reconciliation work? | Record original event time, entrant and reason; whether dual review is required remains TBC. | Administrative Management, Clinical, Finance, Tutor |
| What are retention, accessible-format, translation and representative rules? | Record these as NFR/data-governance gaps; do not assume retention period or channel preference ordering. | Data Protection, Patient Services, Tutor |